## Overview
AI Solution Architecture Advisor POC — Team Task Split
Sprint: Tue 6 Oct → Fri 9 Oct 2026 (demo Friday). Base: existing advisor-poc boilerplate (ADK, mock/Gemini/Ollama) + Updated Requirements doc.
Goal for Friday: all 4 requirement scenarios (A–D) run end to end with the full agent set, brief confirmation, review/rework, dynamic score, human override, and DOCX/PDF export.
Role | Responsibility | Tasks | Est. hrs | Done | Blocked | % done (hrs)
R1 | Agent Engineer – Orchestration & Selection (tech lead) | 7 | 23 | 0 | 0 | 0%
R2 | Agent Engineer – Specialist Agents & Prompts | 11 | 23 | 0 | 0 | 0%
R3 | Backend Dev – Reviewer, Scoring, Report & Audit | 7 | 22 | 0 | 0 | 0%
R4 | QA / Test & Demo Engineer | 8 | 19.5 | 0 | 0 | 0%
All | Whole team (kick-off, demo) | 2 | 2.5 | 0 | 0 | 0%
Total |  | 35 | 90 | 0 | 0 | 0%
Hours per person assume ~6 focused hrs/day Tue–Thu plus Friday for merge, fixes and demo.
Key dates
Tue | Kick-off 11:00; set-up; agent names agreed; baseline run + test matrix
Wed | Core build: selector gating, new agents + mocks, reviewer, scoring, audit log. EOD: `pytest` green in mock mode
Thu | Brief confirmation, override, report diagram/risks, export, prompt tuning, real-model regression
Fri | 12:00 code freeze → bug fixes → 15:00 dry run → demo
Already in boilerplate
Analyzer + clarifying questions, rule-based selector (8 agents), parallel specialists, reviewer with rework cap + escalation, scoring, catalogue guard, Markdown report, SQLite run log, .txt/.pdf/.docx intake, 12 tests.
Deferred (after Friday)
• Role-based access + access-controlled sharing of recommendations (NFR-4, sharing part of US-8)
• Web form UI for structured intake (CLI/JSON form only this week)
• Separate Networking, API, Mobile-architecture and Data-Engineering agents (covered by existing agents for now)
• Deployment to Cloud Run / Vertex AI
How to use
• Fill the yellow 'Assignee (name)' column on Task Plan with each person's name.
• Update 'Status' daily from the dropdown; this page's counts and % update automatically.
• Priority: P0 = must have for Friday demo, P1 = should have, P2 = nice to have (drop first if behind).

## Task Plan
ID | Workstream | Task | Details / Done when | Req. refs | Owner | Owner role | Files | Depends on | Priority | Day | Est. hrs | Status | Assignee (name) | Notes
T01 | Kick-off | Kick-off & environment setup | Walk through the boilerplate; everyone runs `pytest` and `scripts/run.py --all` in mock mode, sets a Gemini key in .env. Agree new agent names (accessibility, reliability, cost, devops, evaluation) so R1/R2 can work in parallel. | — | All | Whole team (kick-off, demo) | .env, README.md | — | P0 | Tue | 1 | Not started
T02 | Orchestration & Selection | Analyzer: add applicability flags + better multi-domain classification | Add `reliability_required`, `cost_relevant`, `accessibility_relevant` to AnalyzerOutput; prompt detects combined domains (e.g. full-stack + cloud). Done when the 5 inputs in Req §8 classify as listed. | FR-2.1–2.3 | R1 | Agent Engineer – Orchestration & Selection (tech lead) | agents/analyzer.py, schemas.py, prompts.py | T01 | P0 | Tue | 3 | Not started
T03 | Orchestration & Selection | Selector: register new specialists and gate them | Add new agents to SPECIALISTS / DOMAIN_RULES; reliability + cost only when flags/cloud say so; accessibility for frontend/mobile; evaluation for aiml. Frontend-only must NOT activate cloud, reliability or cost. | FR-3.1, FR-3.4, FR-6.1–6.4, US-3 | R1 | Agent Engineer – Orchestration & Selection (tech lead) | selector.py | T02 | P0 | Wed | 4 | Not started
T04 | Orchestration & Selection | Brief confirmation step before design | After analysis, show the structured brief and pause; user replies 'confirm' or corrections; specialists run only after confirmation (session-state flag). Mock test must still pass. | FR-1.4, US-1 | R1 | Agent Engineer – Orchestration & Selection (tech lead) | orchestrator.py | T02 | P0 | Wed | 4 | Not started
T05 | Orchestration & Selection | Human override of AI decision | On APPROVED/ESCALATED result accept `override approve¦rework: <reason>`; reason is mandatory; decision written to audit log and shown in report. | US-7, FR-7.6 | R1 | Agent Engineer – Orchestration & Selection (tech lead) | orchestrator.py, storage.py | T13 | P0 | Thu | 4 | Not started
T06 | Orchestration & Selection | Pass only relevant context to each specialist | Slice the brief per agent (e.g. cost agent gets scale/budget, not UI pages) to reduce tokens and noise. | FR-3.3 | R1 | Agent Engineer – Orchestration & Selection (tech lead) | agents/specialists.py | T03 | P1 | Thu | 2 | Not started
T07 | Orchestration & Selection | Structured form intake | Accept a JSON/YAML form (title, users, scale, constraints, compliance, budget) via `run.py --form`; convert to requirement text. Add a sample form under scenarios/. | FR-1.1 | R1 | Agent Engineer – Orchestration & Selection (tech lead) | intake.py, scripts/run.py | T01 | P2 | Thu | 3 | Not started
T08 | Orchestration & Selection | Integration, code review & merge | Review all PRs, merge to main by Fri 12:00 code freeze, resolve conflicts in orchestrator/selector. | — | R1 | Agent Engineer – Orchestration & Selection (tech lead) | — | T03–T22 | P0 | Fri | 3 | Not started
T09 | Specialist Agents | Multi-cloud technology catalogue | Add AWS and Azure categories (compute, data, security, AI) to catalogue.json; confirm catalogue.py check flags unknown tech. | NFR-2, NFR-8, NFR-9 | R2 | Agent Engineer – Specialist Agents & Prompts | data/catalogue.json, catalogue.py | T01 | P0 | Tue | 2 | Not started
T10 | Specialist Agents | Accessibility agent | Focus text: WCAG 2.2 AA, keyboard nav, contrast, ARIA, axe-core/Lighthouse checks. | §7.3, US-3 | R2 | Agent Engineer – Specialist Agents & Prompts | prompts.py (SPECIALIST_FOCUS) | T01 | P0 | Tue | 1.5 | Not started
T11 | Specialist Agents | Reliability agent | HA, fault tolerance, backup, DR, RTO/RPO — only meaningful when infra is in scope; say 'not applicable' otherwise. | FR-6.2 | R2 | Agent Engineer – Specialist Agents & Prompts | prompts.py | T01 | P0 | Wed | 1.5 | Not started
T12 | Specialist Agents | Cost agent | Cost drivers, rough monthly estimate ranges, optimization levers; flag assumptions on pricing. | FR-6.3, NFR-2 | R2 | Agent Engineer – Specialist Agents & Prompts | prompts.py | T01 | P0 | Wed | 2 | Not started
T13 | Specialist Agents | Mock responses for new agents | Canned JSON for accessibility, reliability, cost, devops, evaluation in mock_llm.py so `pytest` and mock runs stay green. | — | R2 | Agent Engineer – Specialist Agents & Prompts | mock_llm.py | T10–T12 | P0 | Wed | 2 | Not started
T14 | Specialist Agents | DevOps/Delivery agent | CI/CD, environments, deployment strategy, release management — where applicable. | §7.3 | R2 | Agent Engineer – Specialist Agents & Prompts | prompts.py | T01 | P1 | Wed | 1.5 | Not started
T15 | Specialist Agents | Evaluation agent (AI solutions) | RAG/LLM evaluation: golden set, groundedness, hallucination rate, latency/cost per query. Needed for Scenario D. | §15 Scenario D | R2 | Agent Engineer – Specialist Agents & Prompts | prompts.py | T01 | P1 | Thu | 1.5 | Not started
T16 | Specialist Agents | Security: compliance mapping | Map named compliance needs (GDPR, SOC 2, HIPAA, PCI-DSS) to controls; never force cloud controls on frontend-only. | FR-5.1–5.4, US-4 | R2 | Agent Engineer – Specialist Agents & Prompts | prompts.py | T01 | P1 | Thu | 2 | Not started
T17 | Specialist Agents | Prompt tuning with Gemini on all scenarios | Every specialist output has rationale, ≥1 alternative per major choice, explicit assumptions. Iterate until Reviewer stops raising 'missing rationale' findings. | FR-4.1–4.5, NFR-3 | R2 | Agent Engineer – Specialist Agents & Prompts | prompts.py | T13, T23 | P0 | Thu | 4 | Not started
T18 | Specialist Agents | Guardrails: scope & refusal | Specialists refuse unsafe/out-of-scope tasks and don't add components outside the confirmed scope. | NFR-9 | R2 | Agent Engineer – Specialist Agents & Prompts | prompts.py | T17 | P1 | Fri | 2 | Not started
T19 | Specialist Agents | Bug fixes from QA run | Fix issues R4 logs on Thu/Fri for specialist outputs. | — | R2 | Agent Engineer – Specialist Agents & Prompts | — | T28 | P0 | Fri | 3 | Not started
T20 | Review, Report & Audit | Reviewer: scope-fit & unnecessary-component checks | Reviewer flags components not justified by the brief, checks tech fits project type, routes findings to new agents by name. | §7.4, FR-7.1–7.4 | R3 | Backend Dev – Reviewer, Scoring, Report & Audit | agents/reviewer.py, prompts.py | T03 | P0 | Wed | 3 | Not started
T21 | Review, Report & Audit | Dynamic quality score | Add accessibility, reliability, cost, maintainability, scalability dimensions; score only applicable ones; weights per project type. | §12 | R3 | Backend Dev – Reviewer, Scoring, Report & Audit | scoring.py, tests/test_scoring.py | T03 | P0 | Wed | 3 | Not started
T22 | Review, Report & Audit | Audit log completeness | Log prompts, agent outputs, every rework iteration and human overrides (new table); `list_runs.py` shows overrides. | NFR-5, US-7 | R3 | Backend Dev – Reviewer, Scoring, Report & Audit | storage.py, scripts/list_runs.py | T01 | P0 | Wed | 3 | Not started
T23 | Review, Report & Audit | Approval rules | APPROVED only if no Critical, no unresolved High (unless overridden), score ≥ threshold, assumptions + rationale present. | §10, US-6 | R3 | Backend Dev – Reviewer, Scoring, Report & Audit | scoring.py, orchestrator.py | T21 | P0 | Thu | 2 | Not started
T24 | Review, Report & Audit | Report: diagram + risk register | Add Mermaid architecture diagram to Solution Design; risks table with severity, likelihood, impact, mitigation, owner. | §11 | R3 | Backend Dev – Reviewer, Scoring, Report & Audit | report.py, schemas.py | T20 | P0 | Thu | 4 | Not started
T25 | Review, Report & Audit | Export to DOCX and PDF | `run.py --export docx¦pdf` produces the 8-part package from the Markdown report. | US-8 | R3 | Backend Dev – Reviewer, Scoring, Report & Audit | report.py, new export.py, requirements.txt | T24 | P1 | Thu | 4 | Not started
T26 | Review, Report & Audit | Bug fixes from QA run | Fix issues R4 logs for reviewer, scoring, report and export. | — | R3 | Backend Dev – Reviewer, Scoring, Report & Audit | — | T28 | P0 | Fri | 3 | Not started
T27 | QA & Demo | Baseline run & gap log | Run pytest, mock `--all` and Gemini `--all`; record which agents fire per scenario, scores, time taken; log gaps for the team. | NFR-1 | R4 | QA / Test & Demo Engineer | outputs/ | T01 | P0 | Tue | 2 | Not started
T28 | QA & Demo | Acceptance test matrix | One row per US-1…US-8 and per Req §8 example: input, expected classification, expected agents, expected status. Shared with all owners. | US-1–US-8, §8 | R4 | QA / Test & Demo Engineer | tests/ (or sheet) | T01 | P0 | Tue | 3 | Not started
T29 | QA & Demo | New scenarios | Add: REST API + PostgreSQL, GCP data pipeline, mobile app, SaaS + AWS (multi-domain), compliance-heavy (GDPR). | FR-2.2, NFR-7, NFR-8 | R4 | QA / Test & Demo Engineer | scenarios/ | T28 | P0 | Wed | 1.5 | Not started
T30 | QA & Demo | Selector tests for all §8 rows | Parametrised tests incl. negative test: frontend-only activates no cloud/reliability/cost agent. | US-2, US-3, FR-6.4 | R4 | QA / Test & Demo Engineer | tests/test_selector.py | T03 | P0 | Wed | 2 | Not started
T31 | QA & Demo | End-to-end mock tests | Rework loop cap, escalation, clarifying questions on vague input (scenario 5), brief confirmation pause. | FR-1.3, FR-7.5–7.6, US-6 | R4 | QA / Test & Demo Engineer | tests/test_pipeline_mock.py | T04, T13 | P0 | Thu | 3 | Not started
T32 | QA & Demo | Real-model regression run | Run every scenario with Gemini after merges; record score, agents, iterations, time; file bugs to R2/R3. | NFR-1, NFR-3 | R4 | QA / Test & Demo Engineer | — | T17, T24 | P0 | Thu | 3 | Not started
T33 | QA & Demo | Override & export checks | Override needs reason and appears in audit log + report; DOCX/PDF open and contain all 8 parts. | US-7, US-8 | R4 | QA / Test & Demo Engineer | — | T05, T25 | P1 | Fri | 2 | Not started
T34 | QA & Demo | Demo script & dry run | Pick 3 scenarios (frontend-only, full-stack+cloud, RAG); talking points per step; dry run 15:00 Fri. | — | R4 | QA / Test & Demo Engineer | — | T08 | P0 | Fri | 3 | Not started
T35 | Kick-off | Friday demo | Code freeze 12:00 → dry run 15:00 → demo. R1 presents architecture, R4 runs scenarios. | — | All | Whole team (kick-off, demo) | — | T34 | P0 | Fri | 1.5 | Not started

## Daily Plan
Role | Tue 6 Oct | Wed 7 Oct | Thu 8 Oct | Fri 9 Oct
R1 – Agent Engineer – Orchestration & Selection (tech lead) | T01 Kick-off & environment setup (1h) T02 Analyzer: add applicability flags + better multi-domain classification (3h) | T03 Selector: register new specialists and gate them (4h) T04 Brief confirmation step before design (4h) | T05 Human override of AI decision (4h) T06 Pass only relevant context to each specialist (2h) T07 Structured form intake (3h) | T08 Integration, code review & merge (3h) T35 Friday demo (1.5h)
R2 – Agent Engineer – Specialist Agents & Prompts | T01 Kick-off & environment setup (1h) T09 Multi-cloud technology catalogue (2h) T10 Accessibility agent (1.5h) | T11 Reliability agent (1.5h) T12 Cost agent (2h) T13 Mock responses for new agents (2h) T14 DevOps/Delivery agent (1.5h) | T15 Evaluation agent (AI solutions) (1.5h) T16 Security: compliance mapping (2h) T17 Prompt tuning with Gemini on all scenarios (4h) | T18 Guardrails: scope & refusal (2h) T19 Bug fixes from QA run (3h) T35 Friday demo (1.5h)
R3 – Backend Dev – Reviewer, Scoring, Report & Audit | T01 Kick-off & environment setup (1h) | T20 Reviewer: scope-fit & unnecessary-component checks (3h) T21 Dynamic quality score (3h) T22 Audit log completeness (3h) | T23 Approval rules (2h) T24 Report: diagram + risk register (4h) T25 Export to DOCX and PDF (4h) | T26 Bug fixes from QA run (3h) T35 Friday demo (1.5h)
R4 – QA / Test & Demo Engineer | T01 Kick-off & environment setup (1h) T27 Baseline run & gap log (2h) T28 Acceptance test matrix (3h) | T29 New scenarios (1.5h) T30 Selector tests for all §8 rows (2h) | T31 End-to-end mock tests (3h) T32 Real-model regression run (3h) | T33 Override & export checks (2h) T34 Demo script & dry run (3h) T35 Friday demo (1.5h)

## Req Coverage
Requirement | Current state in boilerplate | Covered by tasks
FR-1 Requirement intake | Existing: text/PDF/DOCX + clarifying Qs | T04, T07, T31
FR-2 Classification | Existing: domains + confidence | T02, T30
FR-3 Dynamic orchestration | Existing: rule table, parallel run | T03, T06
FR-4 Solution design | Existing: SpecialistOutput schema | T17, T24
FR-5 Security | Existing: security focus | T16
FR-6 Perf / reliability / cost | Partial: performance only | T03, T11, T12
FR-7 Review & rework | Existing: cap + escalate | T20, T23, T31
§10 Approval criteria | Partial | T23
§11 Recommendation package | Partial: Markdown, no diagram/risk owner | T24, T25
§12 Dynamic quality score | Partial: fewer dimensions | T21
NFR-1 Performance | Not measured | T27, T32
NFR-2 / NFR-9 Catalogue & guardrails | Existing: GCP-only catalogue | T09, T18
NFR-3 Explainability | Partial | T17
NFR-4 Security / RBAC | Not started | Deferred
NFR-5 Auditability | Partial: run log only | T22
NFR-6 Extensibility | Existing: one-template specialists | T03
NFR-7 Multi-domain | Partial | T02, T29
NFR-8 Multi-cloud | GCP only | T09, T29
US-1 Plain-language input + brief | Partial | T04
US-2 Explainable agent selection | Existing | T30
US-3 Frontend-only avoids cloud | Existing (cloud gate) | T03, T30
US-4 Security & compliance | Partial | T16
US-5 Perf/reliability/cost when relevant | Partial | T11, T12
US-6 Reviewed before shown | Existing | T23, T31
US-7 Human override with reason | Not started | T05, T22, T33
US-8 Export & share | Markdown only | T25, T33 (sharing deferred)